## Upload Instructions
With the Event Import feature, you can easily transfer all your information into Propared without missing a beat. Here's a couple tips to ensure the best possible upload of your data.
1. All files must be in .csv format.
2. You DON'T need every field filled out for every event. Don't know a start or end time? Date? Team members? Not a problem. We'll map everything you have even if there are fields left blank.
3. We recommend you use the sample template provided. The columns perfectly map to the existing field values in the program. If you have customized columns that are different, don't worry. You can map these to their appropriate fields in Propared or choose to leave them out of the import.
4. Don't forget to spellcheck! Any existing contact, location, department, or category in your Portfolio will get automagically mapped… provided the spellings match! Do a once over on your schedule to avoid any errors. If you do happen to miss something, it's all good. We'll still map that information to the "Details" field. You'll then be able to go in and make the changes you need.
5. On that note, if there are contacts, locations, categories, or departments in your document that don't already exist in your Portfolio, we'll add them into the "Details" field as well. This way, you have a reminder you to create those records later and do a bulk edit.
6. If you have multiple contacts, locations, categories, or departments attached to a task, separate them using commas to ensure they are all added successfully. See the sample schedule for how to do this.
7. If there are any errors in importing, you'll receive a message once the upload is complete. It will tell you the number of errors and add an "IMPORT ERROR" tag to each task that had an issue. To correct these, simply filter your tasks by the "Import Error" tag to find the trouble spots and make your adjustments!
Let us know if you run into any issues!
-Team Propared

## Sample Schedule
Start Date | Start Time | End Date | End Time | Name | Location | Assigned Team | Categories | Departments | Notes
2016-05-05 |  |  |  | Client travel to NYC | Terminal 1 (JFK) | Seth Rowan | travel
2016-05-05 |  |  |  | VPP & Graphics travel to NYC | Terminal 1 (JFK) |  | travel
2016-05-06 |  |  |  | Rehearsal Space Load In | Studio 1 (Conference Center), Main Tent (Conference Center) |  | rehearsal, load in |  | DVD station setup
2016-05-06 |  |  |  | Client executives travel to NYC | Terminal 1 (JFK) | Lisa Ruiz | travel
2016-05-07 |  |  |  | Prompter Load In | Studio 1 (Conference Center) | Clara Barnett | load in
2016-05-07 | 8a |  |  | Graphics Crew Call | Studio 1 (Conference Center) | Layla Cepada
2016-05-07 | 10a |  | 2p | Executive Rehearsal | Studio 1 (Conference Center) | Clara Barnett, Layla Cepada, Lisa Ruiz | rehearsal
2016-05-08 | 10a |  | 2p | Executive Rehearsal | Studio 1 (Conference Center) | Clara Barnett, Layla Cepada, Lisa Ruiz | rehearsal |  | All VPP now on site
2016-05-09 | 10a |  | 2p | Executive Rehearsal | Studio 1 (Conference Center) | Clara Barnett, Layla Cepada, Lisa Ruiz | rehearsal
2016-05-09 | 10a |  | 1p | Production Meeting | Office (Production Company) | West Palm Productions | meeting | production, talent, venue | All department heads
2016-05-09 |  |  |  | Shop Prep Complete, Trucks Loaded | Shop (Warehouse) |  |  | lighting, audio, scenic, rigging
2016-05-10 |  |  |  | Out of Town Production Crew Travel | Terminal 1 (JFK)
2016-05-10 |  |  |  | Graphics Production Continues
2016-05-10 | 10a |  | 2p | Executive Rehearsal | Studio 1 (Conference Center) | Clara Barnett, Layla Cepada, Lisa Ruiz | rehearsal
2016-05-10 | 31:00 |  | 10p | Load In | Main Tent (Conference Center) |  | load in |  | Office trailer staged
2016-05-10 | 7a |  |  | Extra Tents Delivered |  |  | load in, trucking | tents
2016-05-10 | 7:30a |  |  | Lifts Delivered | Loading Dock (Conference Center) |  | load in, trucking | lifts | 1 truck
2016-05-10 | 7:30a |  |  | Radios Delivered | Loading Dock (Conference Center) |  | load in, trucking | production | 1 van
2016-05-10 | 8a |  |  | Rigging Delivery | Loading Dock (Conference Center) |  | load in, trucking | rigging | 1 truck
2016-05-10 | 8a |  |  | Lighting Delivery | Loading Dock (Conference Center) |  | load in, trucking | lighting | 2 trucks
2016-05-10 | 8a |  |  | Crew Call | Loading Dock (Conference Center) |  | load in, crew | rigging, lighting, production | head +20
2016-05-10 | 8a |  |  | Build & Rig all flown Truss | Main Tent (Conference Center) |  | load in, crew | rigging
2016-05-10 | 8a |  |  | Build LED Truss | Main Tent (Conference Center) |  | load in, crew | rigging
2016-05-10 | 8a |  |  | Hang LED & Flown Truss | Main Tent (Conference Center) |  | load in, crew | lighting
2016-05-10 | 8a |  |  | Softgood Delivery | Loading Dock (Conference Center) |  | load in, trucking |  | 1 truck
2016-05-10 | 10:30a |  |  | Coffee Break |  |  | load in, break | rigging, lighting, production
2016-05-10 | 10:30a |  |  | Pipe & Drape Delivery | Loading Dock (Conference Center)
2016-05-10 | 1p |  | 2p | Meal Break |  |  | load in, break | rigging, lighting, production | Walk away
2016-05-10 | 2p |  | 7p | Load In Continues | Main Tent (Conference Center) |  | load in
2016-05-10 | 2p |  |  | Video Delivery | Loading Dock (Conference Center) |  | load in, trucking | video | 1 truck
2016-05-10 | 2p |  |  | Soft LED Delivery | Loading Dock (Conference Center) |  | load in, trucking | video | 1 truck
2016-05-10 | 2p |  |  | Crew Call | Main Tent (Conference Center) |  | load in, crew | video | head +8
2016-05-10 | 7p |  | 8p | Meal Break |  |  | load in, break | rigging, lighting, video, production | walk away
2016-05-10 | 8p |  | 10p | Continue Load In |  |  | load in | rigging, lighting, video, production
2016-05-10 | 10p |  |  | End of Day |  |  | load in |  | All flown elements in the air
2016-05-10 | 7p | 2016-05-11 | 8a | Overnight Security |  |  | load in |  | 2 security guards
2016-05-13 | 9a |  |  | Production On Site |  | West Palm Productions
2016-05-13 | 9a |  |  | Crew Call |  |  | crew
2016-05-13 | 9a |  | 11a | Final notes
2016-05-13 | 11a |  |  | Final executive rehearsal |  | Clara Barnett, Layla Cepada, Lisa Ruiz | rehearsal
2016-05-13 | 11a |  |  | Band gear delivery | Loading Dock (Conference Center) |  | trucking | band
2016-05-13 | 12p |  | 1p | Meal Break |  |  | break | rigging, lighting, video, production | walk away
2016-05-13 | 1p |  | 2p | Satellite test feed |  |  | tech | video, sound
2016-05-13 | 2p |  |  | Sound Check w/ band |  |  | tech | sound
2016-05-13 | 3:30p |  |  | Sound Check w/ dj |  |  | tech | sound
2016-05-13 | 4p |  |  | Red carpet open for talent arrivals |  |  | show
2016-05-13 | 4p |  |  | Room Ready |  |  | show
2016-05-13 | 4p |  |  | All crew & DJ in position for doors |  |  | show
2016-05-13 | 5p |  |  | Doors |  |  | show
2016-05-13 | 5:45p |  |  | Band stage call |  |  | show
2016-05-13 | 6p |  |  | Band Performance |  |  | show
2016-05-13 | 6:15p |  |  | Executives backstage |  | Lisa Ruiz, Seth Rowan | show
2016-05-13 | 6:30p |  |  | Presentation |  | Lisa Ruiz, Seth Rowan | show |  | See Show Flow
2016-05-13 | 7p |  |  | Show Complete / DJ Starts |  |  | show
2016-05-13 | 9p |  |  | Party Over |  |  | show
2016-05-13 | 10p |  |  | Load Out Begins |  |  | load out
2016-05-13 | 10p |  |  | Load Out Crew Called |  |  | load out | rigging, lighting, video, production
2016-05-13 | 10p | 2016-05-14 | 12a | Decor & Catering Load Out |  |  | load out
2016-05-13 | 10p |  | 11p | Empties return as necessary |  |  | load out
2016-05-13 | 11:30p | 2016-05-14 | 8a | Load Out | Main Tent (Conference Center) |  | load out | rigging, lighting, video, production | LX - clear all stage & floor units. Video - pack video village, cameras, all prompters & plasma screens. Audio - All stage, PA, cable Carp - stage / drape / truss Rig - all truss
2016-05-14 | 1a |  |  | Audio Truck Call | Loading Dock (Conference Center) | West Palm Productions | load out, trucking
2016-05-14 | 2a |  |  | Video truck call | Loading Dock (Conference Center) | West Palm Productions | load out, trucking
2016-05-14 | 5a |  |  | Rigging Truck call | Loading Dock (Conference Center) |  | load out, trucking
2016-05-14 | 8a |  |  | Drape Pickup | Loading Dock (Conference Center) |  | load out, trucking
2016-05-14 | 8a |  |  | Soft LED Pickup | Loading Dock (Conference Center) |  | load out, trucking
2016-05-14 | 8a |  |  | Heavy Equipment Pickup | Loading Dock (Conference Center) |  | load out, trucking
2016-05-14 | 8a |  | 12p | Cleaning crew call |  |  | load out
2016-05-14 | 12p |  |  | Site Clean |  |  | load out

## Schedule Template
Start Date | Start Time | End Date | End Time | Name | Location | Assigned Team | Categories | Departments | Notes